## Feuille 1
Tache | Ressource | time | status | comments
WEB TMA
update website logo (with icon and without stay tuned) | ZN | 2014-07-30 | Prod
Info layer | JX | 2014-08-12
Tracking | JX | 2014-08-14
Facebook comment | JX | 2014-08-19
Tweet it | JX | 2014-08-21
Devices | ZN | 2014-08-15
Seezer+Spotify | JX | 2014-08-28
SEO
W3C errors correction | JX | 2014-07-31 | Local | Task description sent by mail
change categories urls | ZN | 2014-07-31 | local
Top stations : permailnk in subdomain | ZN | 2014-07-31 | Local
change station links | ZN | 2014-07-31 | Local
change podcast links | ZN | 2014-07-31 | Local
301 all existing page | ZN | 2014-07-31 | Local
Static pages : make accessible | ZN | 2014-08-01 | Local
urls max 80 caracteres | ZN | 2014-08-31 | Local
change Titles | ZN | 2014-08-01 | In progress
make desc shorter : max 200 caracters | ZN | 2014-08-01 | In progress
Description in home page | ZN | 2014-08-01 | In progress
Add the API lettre.pro | JX | 2014-07-05 | Merging in progress | Task descripton sent by mail
program guide | JX | 2014-08-08
improve the density of keywords radio, station, radio station, écouter, listen, online, en direct, live | ZN | 2014-08-01 | Local
improve density of couples : écouter radio, radio direct, listen radio, radio online | ZN | 2014-08-01 | Local
Direct categories urls in the home page | ZN | 2014-08-04 | In progress
Tags in home page and catalog | ZN | 2014-08-04 | In progress
have a correct href in javascript links | ZN | 2014-08-04 | In progress
Improve the response time | ZN | 2014-08-06
improve the wight | ZN | 2014-08-06
Monetization
pre-roll video | ZN | 2014-08-12
Fnac banner | ZN | 2014-08-13